## Sheet1
NedPeds Proposed Accelerated Process Schedule- April 22, 2013
Weeks (estimate) | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20
Month | April |  | May |  | June |  | July |  | Aug
Community Meetings, DDA and DAT buy in for preferred 60% design recommendations
NPP 60% Process
RFP Development
Historical Clearance Work/Ruling
Final Design/RFPs* to DDA/BOT
CDOT FOR Meeting
Out to Bid
Final Contracts to DDA/BOT
Biomimicry Meeting
Construction
* RFPs for a Construction Manager and the actual Construction Bids will be presented for up or down votes (may be conditional depending on Historical Clearance)
Specific Dates
NPP 60% Process
DDA Meeting | 2013-04-03
Public/DAT Meeting | 2013-04-14
SAB Meeting | 2013-04-10
PROSAB Meeting | 2013-04-18
BOT | 2013-04-16
TRC Meeting | 2013-04-24
DDA Meeting | 2013-04-24
Planning Commission Meeting | 2013-04-24
BioMimicry Public Meeting | 2013-05-24
Final Approval
DDA RFPs Approval | 2013-05-15 | (Conor out, recommend rescheduling to end of week, beginning of next)
BOT RFPs Approval | 2013-05-21
RFP Release/ Bid Opening | 2013-05-22
Construction Manager Interviews | 2013-06-05
Construction Manager Contract Awarded | 2013-06-12 | Will need to be approved via special meeting or by the town on reccomendation of selection committee
Contractor Interviews | 2013-06-14
DDA Contract Approval | 2013-06-19
BOT Contract Approval | 2013-06-18
Contractor Contract Awarded | 2013-06-28
Construction Schedule
Start Construction | 2013-07-15 | or earlier
Finish Construction | 2013-08-30

## Sheet2
NedPeds Deliberative Process Schedule- August 6, 2013 | [9 empty] | 2014
Month | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July
RFP Development
Historical Clearance Work/Ruling
Xcel Relocation Efforts
Biomimicry Workshop
SAB Scoring
Design/RFPs* to DDA/BOT
CDOT FOR Meeting
Construction Manager Out to Bid
Contractor Out to Bid
DDA Contract Approval
BOT Contract Approval
Construction Starts
Schedule Detail
Date |  |  |  |  | Meeting
Aug/Sep-TBD |  |  |  |  | Biomimicry Workshop
2013-08-21 |  |  |  |  | DDA Meeting -Presentation of 90% Drawings and Final Cost Estimates
2013-08-27 |  |  |  |  | BoT/DDA worksession - Options recommendations
2013-09-09 |  |  |  |  | SAB to Score Project
2013-09-17 |  |  |  |  | BoT Meeting- 90% Approval
2013-09-18 |  |  |  |  | DDA Meeting- 90% Approval
Sep- TBD |  |  |  |  | FOR Meeting
2013-10-16 |  |  |  |  | DDA- Final Design Approval and Construction Manager RFP Approval
2013-10-23 |  |  |  |  | Planning Commission Meeting - Final Approval
2013-11-05 |  |  |  |  | BoT- Final Design Approval and Construction Manager RFP Approval
2013-11-06 |  |  |  |  | Construction Manager out to Bid
2013-12-11 |  |  |  |  | DDA- Construction manager Contract Approval
2013-12-17 |  |  |  |  | BoT- Construction Manager Contract Approval
2013-01-15 |  |  |  |  | DDA- Approval of Construction RFP
2013-01-21 |  |  |  |  | BoT- Construction RFP to BoT for Approval
2013-01-22 |  |  |  |  | Construction Contract out to Bid
2013-02-19 |  |  |  |  | DDA- Construction Contract to DDA for Approval
2013-03-04 |  |  |  |  | BoT- Construction Contract to BoT for Approval

## Sheet3
Required Meeting Schedule
Date | Meeting | C2 Time Est.
2013-06-12 | DDA Meeting - Design Budget, Schedule, Utilities | 2.5
2013-07-17 | DDA Meeting - Utilities, 60% Drainage, Costs | 2.5
2013-08-21 | DDA Meeting - Presentation of 90% Drawings and Final Cost Estimates | 2.5
2013-08-27 | BoT/DDA worksession - Options recommendations | 2.5
2013-09-17 | BoT Meeting- 90% Approval | 2.5
2013-09-18 | DDA Meeting- 90% Approval | 2.5
Sep- TBD | FOR Meeting | 2.5
2013-10-16 | DDA- Final Design Approval and Construction Manager RFP Approval | 2.5
2013-11-05 | BoT- Final Design Approval and Construction Manager RFP Approval | 2.5
2013-11-06 | Construction Manager out to Bid
2013-12-17 | BoT- Construction Manager Contract Approval | 2.5
2013-01-15 | DDA- Approval of Construction RFP
2013-01-21 | BoT- Construction RFP to BoT for Approval
2013-01-22 | Construction Contract out to Bid
2013-02-18 | BoT- Construction Contract to BoT for Approval | 2.5

## Alternate_090413
NedPeds Deliberative Process Schedule- August 6, 2013 | [9 empty] | 2014
Month | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July
RFP Development
Historical Clearance Work/Ruling
Xcel Relocation Efforts
Biomimicry Workshop
PROSAB 90%
SAB 90%
Design/RFPs* to DDA/BOT
CDOT FOR Meeting
Construction Manager Out to Bid
Contractor Out to Bid
DDA Contract Approval
BOT Contract Approval
Construction Starts
Schedule Detail
Date |  |  |  |  | Meeting
Sep/Oct-TBD |  |  |  |  | Biomimicry Workshop
2013-08-21 |  |  |  |  | DDA Meeting -Presentation of 90% Drawings and Cost Estimates
2013-08-27 |  |  |  |  | BoT/DDA worksession - Options recommendations
2013-09-18 |  |  |  |  | DDA Meeting- 90% Approval
2013-09-19 |  |  |  |  | PROSAB 90% meeting
Oct- TBD |  |  |  |  | CDOT FOR Meeting
2013-10-14 |  |  |  |  | SAB 90% meeting
2013-10-15 |  |  |  |  | BoT Meeting- 90% Approval
2013-10-16 |  |  |  |  | DDA- Construction Manager RFP Approval
2013-11-05 |  |  |  |  | BoT - Construction Manager RFP Approval
2013-11-06 |  |  |  |  | Construction Manager out to Bid
2013-11-19 |  |  |  |  | BoT- Final Design Approval
2013-11-20 |  |  |  |  | DDA- Final Design Approval
2013-11-27 |  |  |  |  | Planning Commission Meeting - Final Approval
2013-12-11 |  |  |  |  | DDA- Construction manager Contract Approval
2013-12-17 |  |  |  |  | BoT- Construction Manager Contract Approval
2013-01-15 |  |  |  |  | DDA- Approval of Construction RFP
2013-01-21 |  |  |  |  | BoT- Construction RFP to BoT for Approval
2013-01-22 |  |  |  |  | Construction Contract out to Bid
2013-02-19 |  |  |  |  | DDA- Construction Contract to DDA for Approval
2013-03-04 |  |  |  |  | BoT- Construction Contract to BoT for Approval